## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the proces and include a detailed description of every step. Add reasoning on why you took certain descisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Researched a useful algorithm | 0,5 | 2021-11-13 | I was already aware of the recursive backtracking algorithm to generate a maze, but I was wondering if there were better options. I eventually did choose the recursive backtracking one
Setup a Unity project | 0,5 | 2021-11-13 | Setting up the Unity project basically involved me creating a new project and creating the objects I thought were necessary
Setup the architectural layout of the app | 2 | 2021-11-13 | I always like to create scalable apps, which sometimes require the right approach of the architectural layout of your app. This usually involves applying design patterns, which I did to make the app maintainable, organized and scalable
Setup the UI | 2 | 2021-11-13 | This subject had me setting up the UI and make it responsive with multiple resolutions, but also to pass user input to the maze generation script(s)
Implemented the algorithm | 5 | 2021-11-13 | This one took the longest, because this is the core of the whole app. For every algorithm, you have to create a new script in which all of the logic will be handled for that specific algorithm. During runtime you can switch the algorithm, but for now, there is 1 algorithm implemented
Increased the performance of the algorithm | 2 | 2021-11-15 | Last time I applied at DTT, the performance was not all too great, because every frame a single iteration was executed. Now, it is possible to do multiple iterations per frame, which you can specify in the editor to set how many iterations the algorithm can run per second
Fine-tuned flow and code | 1 | 2021-11-19 | At this point it all worked, but I was not satisfied yet, so I improved the overall flow of the app to make it more accessible and scalable. I also removed redundant code to better improve the code
Created a class diagram | 1,5 | 2021-11-19 | I wanted to get bonus points, so I made a class diagram of the app, which hopefully helps out understanding my decisions I made for this app | x
Added comments in the code | 0,5 | 2021-11-20 | After looking through the document explaining the test, I noticed it was advisable to add comments to the code. For this reason I added it
Total amount of hours | 12